## Content Plan
Content Plan & Deadline Pre-Event Triatra – November 2026
Aturan: desain H-3, approval H-2. Story live maks. 2 jam setelah pertandingan, recap feed maks. H+1.
No | Tanggal Upload | Konten | Format | Isi Singkat | Deadline Desain | Deadline Approval | PIC | Status
1 | 1 Nov | Kick-off Fun Fresh: Run & Walk | Feed + Story + Frame | Poster + frame, ajak upload & tag akun | 31 Okt (pagi) | 31 Okt (sore) |  | Belum
2 | 2 Nov | ML Penyisihan dimulai | Feed + Story | Poster + bracket | 31 Okt | 1 Nov |  | Belum
3 | 2 Nov | Display Streaming ML | Overlay + Waiting Room Stream | Overlay stream & konten waiting room | 31 Okt | 1 Nov |  | Belum
4 | 3–6 Nov | Update ML harian | Story | Hasil match (pakai template) | 3 Nov | 4 Nov |  | Belum
5 | 8,15,22,29 Nov | Fun Fresh Weekly | Story | Repost peserta + leaderboard (template) | 3 Nov | 4 Nov |  | Belum
6 | 9 Nov | H-1 Futsal & Badminton | Feed + Story + Frame | Poster + reminder | 6 Nov | 7 Nov |  | Belum
7 | 10–11 Nov | Futsal & Badminton | Story (live) | Highlight & skor | Hari-H | Hari-H |  | Belum
8 | 12 Nov | Recap Futsal & Badminton | Feed (carousel) | Foto + pemenang (template recap) | 9 Nov | 10 Nov |  | Belum
9 | 12 Nov | Teaser Brain Battle | Feed + Story + Frame | Poster Brain Battle | 9 Nov | 10 Nov |  | Belum
10 | 13 & 20 Nov | Brain Battle | Story | Reminder pagi, highlight sore | Hari-H | Hari-H |  | Belum
11 | 16 Nov | Famgath Ancol | Feed + Reels + Story | Dokumentasi | 15 Nov (editing) | 16 Nov |  | Belum
12 | 21 Nov | Recap Brain Battle | Feed | Pemenang | Hari-H | 21 Nov |  | Belum
13 | 22 Nov | H-1 ML Final | Feed + Story | Poster Grand Final, finalis | 19 Nov | 20 Nov |  | Belum
14 | 23–24 Nov | ML Final | Story + Display Streaming | Live update | Hari-H | Hari-H |  | Belum
15 | 25 Nov | Juara ML | Feed | Pengumuman juara | 24 Nov | 24 Nov |  | Belum
16 | 27 Nov | Reminder Video Submission | Story | Deadline 30 Nov | 25 Nov | 26 Nov |  | Belum
17 | 30 Nov | Penutupan Pre-Event | Feed + Story | Recap Fun Fresh + leaderboard akhir | 28 Nov | 29 Nov |  | Belum